# Standard Operating Process for Grant Finding

- Purpose:

This SOP explains how IIAL finds, screens, and qualifies external funding opportunities. Grant finding is a continuous activity. The end product of this process is a short opportunity brief and a go/no-go decision from leadership. Approved opportunities move to another process for writing.

- Pipeline Log:

Follow the excel sheet that has been used in the past (file name: Funding-Opportunities-Programs in Google Drive)

(add in where to look)

- Stage 1: Fast screening

Filter 1: Legal eligibility. Can a federally incorporated Canadian nonprofit (not a charity, not a municipality, not a university) participate in any role at all? If no: no-go.

Filter 2: What role can IIAL play? Classify the opportunity:

- Lead: IIAL applies directly. (Example: CEDF.)

- Funded partner: an eligible entity, usually a municipality, applies as lead, and IIAL is written into the budget as the research or delivery partner, paid from the grant. (Example: the GMF model with the City of Toronto or City of Barrie.) This is a proven IIAL pathway and often the best one. Do not treat it as second prize.

- Unfunded subcontractor or no role: no-go, unless there is a strategic reason to participate anyway. That exception needs a high ROI if there is no financial gains to be made.

Filter 3: Do the money math.

- What is the maximum grant?

- What is the cost-share, and who carries it? Example: GMF Study to Adaptation Action covers 80% up to $70,000, which means the lead municipality pays 20%.

- If IIAL leads, what matching is required, and what are the in-kind limits? Example: CEDF required matching of at least 50% of the grant request, and in-kind contributions could cover at most half of that match.

- VERIFY with management whether IIAL can actually cover any required cash match. Never assume cash is available.

Filter 4: Strategic fit. Does the opportunity map onto at least one existing IIAL capability: WCIS and supply chain integrity, certifications and micro-credentials, applied research and feasibility studies, smart cities and AIoT, climate and sustainability, or international development in countries where relationships already exist? If winning would require inventing a new capability that does not fit into the future of IIAL: no-go.

Filter 5: Is there enough runway? Minimum working time before a fixed deadline: 4 weeks if IIAL is the lead, 8 or more weeks if a partner has to apply, because municipal sign-off cycles are slow and outside IIAL's control. Rolling intakes pass this filter automatically.

Filter 6: Is it worth the effort? Estimate the writing effort against the grant size and the realistic chance of winning.

3.2 Stage 2: Deep qualification

3.2.1 Read program documents

3.2.1.1 Read the full authoritative funder page.

3.2.1.2 Download the official application guide PDF if applicable.

3.2.1.3 Write down the exact words: eligibility clauses, mandatory components of the project, evaluation criteria and weights, reporting and recognition obligations, any limitations with stacking other funding.

3.2.1.4 Note the application structure

3.2.2 Partner pathway analysis (IIAL funded partner)

3.2.2.1 Identify relevant partners where applicable: Does this grant require partners? If so, what contacts can we utilize? If we don’t need a partner, skip this step.

3.2.2.2 Find the right point of contact for the relevant partner. Tailor a pitch to their organization goals (search their website or socials for context)

3.2.2.3 Ensure the pitch is approved before reaching out to the partner. Clarify costs and the ask of the partner so it is a strong pitch.

3.2.3 Budget IIAL’s costs accordingly

3.2.2.1 Ensure that the following is laid out plainly:

- Grant request amount

- IIAL’s revenue from the project

- IIAL’s costs: staff time, platform, travel

3.2.2.2 Ensure the costs required for any matching and in-kind structures are well within IIAL’s capacity. For example, IIAL’s in-kind inventory generally includes: leadership staff time, the IIAL and learn.iial.ca platform, organizational networks and partnerships, and applied research capacity.

3.2.2.3 Verify the team capacity for the delivery window against current commitments (active campaigns, events, international deals).

3.2.4 Current state verification:

| What to confirm | Who confirms it |
| --- | --- |
| Partnerships or MOUs cited | Direct check with MOU or with relationship owner |
| Named point of contacts from partner organizations | Direct check or with the relationship owner |
| IIAL’s strategic priorities | Leadership team |
| Team capacity in the delivery window | Clarissa Getigan, Principal of Sustainability and Partnerships |
| Cash availability for any required match | Dr. Juan Marcelo Gomez, Principal Executive & Founder |
| No other IIAL application is in flight with the same funder or an organization the current grant states cannot be funded in conjunction with | Use the grant log or reach out to leadership team |

3.3 Stage 3: A short opportunity brief

Use the headers below to outline the grant requirements required for leadership's sign-off to move forward.

- Program Snapshot:

  - Funder | Program name | Authoritative URL | Max amount | Cost-share / match | Intake | Deadline | Application structure: one-stage / two-stage (EOI first)

- IIAL Role:

  - Lead applicant

  - Funded partner

  - Other

- Strategic Angle:

  - The IIAL capability this program leverages and what we gain. Example: WCIS framed as a supply chain traceability framework enabling wider audience in Canada

- Mandatory components:

  - Required studies, assessments, deliverables named in the guide

- Money:

  - Request amount | IIAL net revenue | Match required | In-kind cap

- Risks and unknowns:

  - Eligibility ambiguities, capacity constraints, questions arising from program guide

- Recommendation:

  - Go / No-go/ Go- conditional with reason

3.4 Stage 4: Go/No-go

APPROVAL REQUIRED: Present findings to leadership to ensure there is no wasted effort. Nothing moves forward without approval.

3.4.1 Three outcomes:

- Go: Move to SOP: Grant Writing and Submission

- No-go: Log reason. Programs reopen and IIAL’s capabilities grow, so no today might become a yes next year.

- Go-conditional: Proceed if condition is met, track condition and confirm with leadership.

End of SOP. Approved briefs proceed to SOP: Grant Writing and Submission.